## Sheet1
The “EriTufJohMik’ Project re Mental Health Trends in Technology
id | task description | status | responsibility | scheduled date | completed date
10 | Establish base starting point from 2014 Mental Health Survey | WIP | responsibilities
10.1 | - summarise findings from 2014 Mental Health Survey |  | timelines
10.2 | - summarise data sources for 2014 Mental Health Survey |  | to be agreed
10.3 | - provide references for 2014 Mental Health Survey |  | team
to maximise
20 | Combine JHU data sets | WIP | our productivity
20.1 | - debug the code to download and combine the csv files |  | and effectiveness
20.2 | - test and verify that the code works reliably (we will need to run it frequently thoughout the project on different data sets)
20.3 | - process the JHU datasets for 11-01-2021 t0 12-15-2021 and combine them into one csv file and a JHU_Covid dataframe
30 | Process the JHU Covid dataframe | WIP
30.1 | - agree what statistical analysis to use on the JHU_Covid dataframe
30.2 | - conduct statistical analysis on the JHU_Covid dataframe
40 | Process the vaccination data set | WIP
40.1 | - convert the vaccination dataset into a dataframe
40.2 | - agree what statistical analysis to use on the vaccination_dataframe
40.3 | - conduct statistical analysis on the vaccination_dataframe
50 | Process the world population data set | WIP
50.1 | - convert the world_population dataset into a dataframe
50.2 | - agree what statistical analysis to use on the world_population_dataframe
50.3 | - conduct statistical analysis on the world_population_dataframe
60 | Check all dataframes for anomalies / outliers / faulty data / inconsistencies | WIP
60.1 | - JHU_Covid dataframe
60.2 | - vaccination_dataframe
60.3 | - world_population_dataframe
70 | Look for trends in the statistical analysis for all dataframes | WIP
70.1 | - Covid case rates for the selected countries
70.2 | - Covid death rates for the selected countries
70.3 | - Covid vaccination rates for the selected countries
70.4 | - Covid recovery rates for the selected countries
70.5 | - Covid hospitalisation rates for the selected countries (if we can easily get it)
70.6 | - Covid case / fatality rates for the selected countries
80 | Prepare datasets for visualisation | WIP
90 | Prepare presentation materials | WIP
100 | Walk through presentation to confirm its format / content | all |  | 2022-01-03
110 | Rehearse the presentation and familiarise | all |  | 2022-01-03
110 | Group presentation | all |  | 2022-01-04
120 | Try and use JHU APIs along the way (optional) | all
120.1 | - perhaps we could use the JHU API to dynamically pull a geospatial visual as part of our presentation
Legend: WIP work in process,